## Sheet1
WBS | Name | Duration | Effort | Responsibility | Finish
1 | Develop Project Idea | 4 weeks | 15.1 hrs | All team members | 2014-10-13
2 | Develop Project Charter | 1 day | 8.3 hrs | All team members | 2014-10-20
3 | Project charter | 0 |  |  | 2014-10-21
4 | Discuss Plans about LED display | 1 day | 4 hrs | All team members | 2014-10-22
5 | Discuss Plans about Data Glove | 1 day | 4 hrs | All team members | 2014-10-23
6 | Find and Order Parts for LED display | 1 day | 2 hrs | Jose, Kevin | 2014-10-25
7 | Find and Order Parts for Data Glove | 1 day | 2 hrs | Jose, Kevin | 2014-10-25
8 | Finalize plans of LEDs and Data glove | 0 |  |  | 2014-10-28
9 | Plan and write down the Finite State Machine | 2 days | 4 hrs | Robert, Naren | 2014-10-31
10 | Conceptualize the Finite State Machine | 0 |  |  | 2014-11-04
11 | Design and Build LED Hardware | 4 days | 8 hrs | Naren, Kevin | 2014-11-08
12 | Design and Build interface between LEDs and mBed | 2 days | 4 hrs | Robert, Jose | 2014-11-06
13 | Write Drivers to control individual LEDs on the display | 2 days | 4 hrs | Robert, Jose | 2014-11-08
14 | Write Drivers for mBed to take commands to change LED states | 2 days | 4 hrs | Kevin, Naren | 2014-11-10
15 | Debug Driver Software | 1 day | 8 hrs | All team members | 2014-11-11
16 | Processor should be able to control the LEDs | 0 |  |  | 2014-11-11
17 | Write software to receive Dataglove information and send to LED mBed | 2 days | 4 hrs | Robert, Kevin | 2014-11-16
18 | Data Glove communication with the board | 0 |  |  | 2014-11-18
19 | Develop processing software to process dataglove data and transform to LED | 1 week | 10 hrs | Jose, Naren | 2014-11-24
20 | Glove is able to control the LEDs | 0 |  |  | 2014-11-25
21 | Verify system with a simulated environment representing glove movements | 1 week | 10 hrs | Robert, Naren | 2014-12-05
22 | Test physical system | 3 days | 6 hrs | Kevin, Jose | 2014-12-05
23 | Test and Verification of the System | 0 |  |  | 2014-12-05
24 | Debug System Prototype | 4 weeks | 80 hrs | All team members | 2014-12-16
25 | Optimize Code | 2 weeks | 20 hrs | All team members | 2014-12-16
26 | Improve Code Functionality | 2 weeks | 20 hrs | All team members | 2014-12-16
27 | System is working with final requirements | 0 |  |  | 2014-12-16
28 | Create PowerPoint Presentation | 4 days | 5 hrs | All team members | 2014-12-16
29 | Develop final report | 1 week | 10 hrs | All team members | 2014-12-16
30 | Final presentation and demo | 0 |  |  | 2014-12-17
31 | Film Video | 1 day | 4 hrs | All team members | 2014-12-13
32 | Edit Video | 5 days | 3 hrs | Jose | 2014-12-19
33 | Finalize Project Report | 1 day | 4 hrs | All team members | 2014-12-19
34 | Video and project report completed. | 0 |  |  | 2014-12-19